Khmer Sign Language AI Demo Prototype

30-Day Implementation Plan and Weekly Follow-Up Progress Report

Python + Next.js + Project Database Integration

| Project | KSL keypoint extraction and gesture prediction demo prototype |
| --- | --- |
| Core files | landmark_extract.ipynb, best_model_25class_fix.h5, label_map_25class.json |
| Model baseline | 30-frame sequence input, 252 features per frame, 25 output classes |
| Primary stack | Python backend, Next.js frontend, PostgreSQL/project database |
| Planning duration | 30 calendar days / 4 weekly follow-ups |
| Document version | v1.0 |

Document purpose This document converts the prototype idea into a delivery-ready plan: scope, architecture, database model, 30-day schedule, weekly report templates, risks, acceptance criteria, and final demo checklist.

# 1. Executive Summary

The goal of this 30-day plan is to build a demo prototype that proves the trained KSL model can be integrated into the learning platform. The prototype will capture hand keypoints, build a 30-frame sequence, send the sequence to a Python inference service, predict a Khmer sign label, display the prediction in Next.js, and store the prediction result in the project database.

The available model assets strongly define the technical target: the inference input must match 30 frames by 252 features, and the output must map correctly to the 25 labels in the label map. The highest priority is therefore model-input compatibility before UI polish.

## 1.1 Success Definition

A user can open the demo page and allow camera access.

The system detects hand landmarks and constructs a valid 30-frame keypoint sequence.

The Python backend loads the trained model and returns prediction results.

The Next.js frontend displays the predicted Khmer label, confidence score, and top-3 predictions.

Each prediction result is saved to the project database for traceability and future evaluation.

The demo can be presented without manually running the notebook.

# 2. Available Project Assets

| Asset | Type | Prototype Usage |
| --- | --- | --- |
| landmark_extract.ipynb | Notebook | Contains keypoint extraction logic, feature configuration, sequence length, MediaPipe setup, and extraction workflow. |
| best_model_25class_fix.h5 | Keras model | Trained model for 25-class sequence classification. Inspected input layer indicates shape: 30 frames x 252 features. |
| label_map_25class.json | Label map | Maps class labels to numeric indices from 0 to 24, including No_action and 24 Khmer classes. |

## 2.1 Model Baseline

| Item | Value | Implication |
| --- | --- | --- |
| Input shape | 30 x 252 | The backend must produce exactly this sequence shape before prediction. |
| Sequence length | 30 frames | Capture buffer should collect 30 processed frames. |
| Per-frame feature dimension | 252 | Current usable setup is hands only + velocity: 126 hand position features doubled by velocity. |
| Output classes | 25 | Class index must be mapped to Khmer label using the label map. |
| Recommended confidence threshold | 0.60 initial | Below threshold, frontend should show a retry/uncertain result message. |

## 2.2 Label Classes

| Index | Label |
| --- | --- |
| 0 | No_action |
| 1 | កាតាប |
| 2 | កាតាបស្ពាយក្រោយ |
| 3 | កុំព្យូទ័រ |
| 4 | កៅអី |
| 5 | ក្ដារខៀន |
| 6 | ខ្មៅដៃ |
| 7 | ជ័រលុប |
| 8 | ដីស |
| 9 | តុ |
| 10 | ទឹកលុប |
| 11 | នាយករង |
| 12 | នាយិកា |
| 13 | បន្ទាត់ |
| 14 | ប៊ិក |
| 15 | ប៊ិកក្រហម |
| 16 | ប៊ិកខៀវ |
| 17 | លោកគ្រូ |
| 18 | សាលារៀន |
| 19 | សៀវភៅ |
| 20 | សៀវភៅពុម្ភ |
| 21 | ហ្វឺតក្រហម |
| 22 | ហ្វឺតខៀវ |
| 23 | ហ្វឺតខ្មៅ |
| 24 | អ្នកគ្រូ |

# 3. Prototype Scope

## 3.1 In Scope

Python inference service for loading model and label map.

MediaPipe keypoint extraction and feature formatting based on the notebook logic.

30-frame sequence buffer for prediction.

Next.js camera demo page with status flow and result display.

Project database logging for prediction sessions and prediction events.

Basic confidence threshold, No_action fallback, and error states.

Final demo script and progress report.

## 3.2 Out of Scope for the 30-Day Demo

Full production-level training pipeline.

Automatic model retraining from user-submitted data.

Large-scale evaluation dashboard.

Raw video storage without user consent.

Advanced adaptive lesson recommendation logic.

Mobile application packaging.

# 4. Recommended System Architecture

The prototype should use a simple split architecture: Next.js handles camera UI and user interaction, while Python handles MediaPipe extraction and AI inference. The project database becomes the source of truth for class metadata, model version, prediction sessions, and prediction results.

Next.js Frontend - Camera preview - Capture status - Result card - Retry / Continue actions ¦ ¦ REST or WebSocket v Python Backend - MediaPipe keypoint extraction - 30-frame sequence buffer - 252-feature formatter - Keras model inference - Top-k result generation ¦ v Project Database - Model versions - Gesture classes - Prediction sessions - Prediction events

## 4.1 Recommended Demo State Flow

IDLE - HAND_DETECTED - CAPTURING_30_FRAMES - PREDICTING - RESULT_DISPLAYED - USER_RETRY / CONTINUE

This flow is intentionally simple for the first working demo. After it is stable, it can be upgraded to a live-preprediction flow where users see a preliminary result before locking the final result.

# 5. Database-First Integration Plan

The database should not be an afterthought. It should store model metadata, gesture labels, prediction sessions, and prediction events so the prototype is measurable and auditable.

| Table | Purpose | Important Fields |
| --- | --- | --- |
| gesture_classes | Stores the 25 class labels from the label map. | id, class_index, label_kh, is_active, created_at |
| model_versions | Tracks the model used by the prototype. | id, model_name, model_file_path, input_sequence_length, input_feature_dim, output_classes, is_active |
| prediction_sessions | Represents one user demo/practice session. | id, user_id/guest_id, started_at, ended_at, device_info |
| prediction_events | Stores each model prediction result. | id, session_id, model_version_id, predicted_label, confidence, top_k_predictions, inference_ms |
| keypoint_captures | Optional table for debugging or consent-based data contribution. | id, prediction_event_id, keypoints_json/storage_url, consent_given |

Privacy rule For the demo, store prediction results by default. Store keypoints only when needed for debugging or community data contribution, and only after explicit user consent. Avoid storing raw webcam video in the prototype.

# 6. API Contract

| Method | Endpoint | Purpose |
| --- | --- | --- |
| GET | /health/model | Check whether model and label map are loaded. |
| POST | /predict | Send a 30 x 252 sequence and return prediction result. |
| POST | /prediction-sessions | Create a session record for a demo/practice attempt. |
| POST | /prediction-events | Save prediction result, confidence, top-k classes, and inference time. |
| GET | /gesture-classes | Return class metadata from the database. |

## 6.1 Recommended Prediction Response

{ "predicted_class_index": 3, "predicted_label": "កុំព្យូទ័រ", "confidence": 0.87, "top_k": [ { "label": "កុំព្យូទ័រ", "confidence": 0.87 }, { "label": "សៀវភៅ", "confidence": 0.08 }, { "label": "ប៊ិក", "confidence": 0.03 } ], "inference_ms": 42, "sequence_shape": [30, 252] }

# 7. 30-Day Implementation Plan

The schedule is divided into four weekly milestones. Each week ends with a formal follow-up report and a clear go/no-go checkpoint.

| Week | Theme | Milestone |
| --- | --- | --- |
| Week 1 | Foundation and validation | Model loads, label map loads, feature shape verified, backend structure created. |
| Week 2 | Backend inference and keypoints | MediaPipe extraction, 30-frame buffer, feature formatter, prediction API. |
| Week 3 | Next.js demo and database | Camera UI, frontend-backend connection, prediction logging. |
| Week 4 | Stabilization and demo readiness | All-class testing, confidence threshold, final report, presentation script. |

| Day | Task | Expected Output |
| --- | --- | --- |
| 1 | Review files and model assets | Technical notes on notebook, model, and label map |
| 2 | Confirm model input/output shape | 30 x 252 input and 25-class output verified |
| 3 | Create Python inference module structure | ai_inference package skeleton |
| 4 | Implement model and label map loaders | Model loads without crash |
| 5 | Convert notebook extraction logic | Reusable keypoint_extractor.py |
| 6 | Create dummy-sequence prediction test | Prediction function returns index, label, confidence |
| 7 | Week 1 review | Week 1 progress report and risk update |
| 8 | Implement MediaPipe extraction | Hand landmarks extracted from camera/video frame |
| 9 | Build 252-feature formatter | One frame returns exact 252 features |
| 10 | Implement 30-frame sequence buffer | Valid 30 x 252 sequence ready for model |
| 11 | Create /predict endpoint | Backend accepts sequence and returns prediction |
| 12 | Create /health/model endpoint | Model status endpoint available |
| 13 | Test backend with webcam/sample input | End-to-end backend test results |
| 14 | Week 2 review | Week 2 report and backend stabilization plan |
| 15 | Create Next.js demo page | /demo/ksl-prediction route |
| 16 | Build camera permission and preview UI | Webcam preview works |
| 17 | Add status flow | Idle, capturing, predicting, result states |
| 18 | Connect frontend to backend API | Prediction result appears in UI |
| 19 | Create DB migration/schema | Model, class, session, event tables created |
| 20 | Save prediction events | Database logging works |
| 21 | Week 3 review | Week 3 report and UI improvement list |
| 22 | Test available classes | Manual test matrix created |
| 23 | Tune confidence threshold | Low-confidence result behavior defined |
| 24 | Add No_action fallback | No hand/no sign handling improved |
| 25 | Add error/loading states | Stable user experience |
| 26 | Prepare demo script | Presenter guide ready |
| 27 | Fix edge cases | Demo bug-fix pass |
| 28 | Run final internal demo | Demo-ready prototype |
| 29 | Prepare final report | Final progress report draft |
| 30 | Final presentation and handover | Prototype delivered |

# 8. Weekly Follow-Up Progress Report Plan

Each weekly report should be written as a concise project status update. The report should show completed work, in-progress tasks, blockers, risks, next-week priorities, and overall status.

## Week 1 Follow-Up Summary

Focus: Validate the model files, label map, and backend foundation.

| Category | Details |
| --- | --- |
| Completed | Reviewed notebook, model, and label map. |
| Completed | Confirmed model input/output requirements. |
| Completed | Created backend inference module plan. |
| Completed | Identified label-order and feature-format risks. |
| Next | Implement keypoint extraction service. |
| Next | Implement sequence buffer. |
| Next | Build prediction API. |
| Next | Test prediction with dummy and sample keypoints. |
| Overall Status | Yellow - model compatibility must be proven before frontend work. |

## Week 2 Follow-Up Summary

Focus: Build backend keypoint extraction and inference pipeline.

| Category | Details |
| --- | --- |
| Completed | Implemented MediaPipe extraction. |
| Completed | Created 252-feature formatter. |
| Completed | Created 30-frame sequence buffer. |
| Completed | Created /predict API and top-k response. |
| Next | Build Next.js camera page. |
| Next | Connect frontend to backend. |
| Next | Create database migration. |
| Next | Start prediction logging. |
| Overall Status | Yellow - backend works, but real-time frontend testing is pending. |

## Week 3 Follow-Up Summary

Focus: Integrate frontend demo and database logging.

| Category | Details |
| --- | --- |
| Completed | Created camera demo page. |
| Completed | Connected frontend to prediction endpoint. |
| Completed | Added result card and retry flow. |
| Completed | Saved prediction events to database. |
| Next | Test all classes. |
| Next | Add confidence threshold. |
| Next | Improve No_action handling. |
| Next | Prepare final demo script. |
| Overall Status | Green/Yellow - functional prototype exists but needs stabilization. |

## Week 4 Follow-Up Summary

Focus: Stabilize the prototype and prepare the final presentation.

| Category | Details |
| --- | --- |
| Completed | Tested the demo flow. |
| Completed | Added low-confidence and No_action handling. |
| Completed | Improved UI states. |
| Completed | Prepared final report and demo script. |
| Next | Improve dataset collection. |
| Next | Create evaluation dashboard. |
| Next | Prepare retraining pipeline. |
| Next | Upgrade to production architecture. |
| Overall Status | Green - demo prototype is ready with documented limitations. |

# 9. Weekly Progress Report Template

Use this template for formal weekly submission to an advisor, supervisor, or project reviewer.

Project Name: Khmer Sign Language AI Demo Prototype Reporting Period: Week __ / Date: __ to __ Prepared By: Kimhour 1. Summary of Progress This week, the project focused on ________________________________. The main completed work includes ________________________________. The current prototype status is ________________________________. 2. Completed Tasks - - - 3. In-Progress Tasks - - - 4. Technical Progress Frontend: - Backend: - AI Model: - Database: - 5. Issues / Blockers Issue: Impact: Action Needed: 6. Risk Status - Model/keypoint format mismatch: Low / Medium / High - Real-time performance issue: Low / Medium / High - Prediction accuracy limitation: Low / Medium / High - Dataset/class imbalance: Low / Medium / High 7. Next Week Plan - - - 8. Support Needed - 9. Overall Status Green / Yellow / Red Status Explanation: The project is currently __________ because __________________________.

# 10. Risk and Mitigation Plan

| Risk | Level | Impact | Mitigation |
| --- | --- | --- | --- |
| Keypoint format mismatch | High | Model predicts incorrectly even when UI works. | Verify exact 30 x 252 format before UI integration. |
| Label order mismatch | High | Wrong Khmer label may be displayed. | Validate class index against known sample predictions and label map. |
| Real-time webcam performance | Medium | Capture and prediction may feel slow. | Use frame skipping, efficient buffering, and backend profiling. |
| Poor lighting or hand out of frame | Medium | Hand detection may fail or return weak prediction. | Add user guidance, no-hand state, and retry behavior. |
| Low model confidence | Medium | User may receive uncertain prediction. | Use confidence threshold and top-k display. |
| Privacy issue from raw data storage | High | User trust and compliance risk. | Store prediction events by default; require consent for keypoint capture. |
| Environment mismatch | Medium | Model may fail to load on another machine. | Pin TensorFlow, Python, MediaPipe, and NumPy versions. |

# 11. Acceptance Criteria

| Area | Acceptance Criteria | Priority |
| --- | --- | --- |
| Model loading | The Python service loads the .h5 model and label map successfully. | Required |
| Input formatting | The system creates a sequence with shape 30 x 252. | Required |
| Prediction | The backend returns class index, Khmer label, confidence, and top-k predictions. | Required |
| Frontend UI | The demo page shows camera, capture status, and result card. | Required |
| Database logging | Prediction sessions and events are stored. | Required |
| Fallback behavior | No_action, no hand, and low-confidence states are handled. | Required |
| Demo stability | The full flow can run without using the notebook manually. | Required |

# 12. Final Demo Checklist

[ ] Python inference service starts successfully.

[ ] Model loads successfully.

[ ] Label map loads correctly.

[ ] MediaPipe keypoint extraction works.

[ ] Feature vector dimension is exactly 252 per frame.

[ ] Sequence length is exactly 30 frames.

[ ] Backend prediction endpoint returns valid JSON.

[ ] Next.js camera preview works.

[ ] Frontend displays predicted Khmer label.

[ ] Frontend displays confidence score and top-3 predictions.

[ ] Prediction events are saved to database.

[ ] Low-confidence result shows retry guidance.

[ ] No_action/no-hand behavior is handled.

[ ] Demo script is prepared.

[ ] Known limitations are documented.

# 13. Demo Presentation Script

Open the KSL learning platform and navigate to the AI demo/practice page.

Explain that the model uses keypoints rather than raw video for prediction.

Allow camera permission and show the camera preview.

Perform one sign clearly inside the camera frame.

Show the system status changing from capturing to predicting.

Show the predicted Khmer label, confidence score, and top-3 predictions.

Open the database or admin/log view to show the prediction event was saved.

Explain current limitations and the next improvement plan.

# 14. Project Manager Recommendation

Priority sequence Do not start with UI polish. First prove the model pipeline: keypoints -> 30 x 252 sequence -> prediction -> label mapping. After that, build the frontend and database logging around the verified pipeline.

The most important technical milestone is simple: Python must produce a valid prediction from a 30 x 252 keypoint sequence using the existing model and label map. Once that is stable, the remaining work becomes product integration and demo refinement.

# 15. Inspiration design